## Template
STAKEHOLDERS ANALYSIS
Date:
Project: | [10 empty] | Technical
|  |  | mark with an 'X' the level of project support by stakeholder | [7 empty] | Political
Role | Name | Function | Strongly against | Moderatly Against | Neutral | Moderatly Supportive | Strongly Supportive | Nature of resistance (Technical, Political, Cultural, Personal) | Influence (High,Medium, Low) | Influence strategy | Cultural
Sponsor | Mrs … | [9 empty] | Personal
Financial Controller | Mr … | [9 empty] | Low
Stakeholder 1 | [10 empty] | Medium
Stakeholder 2 | [10 empty] | High
Stakeholder 3
Stakeholder 4
Stakeholder 5
Process Owner
Team member 1
Team member 2
Team member 3
Team member 4
Team member 5
Highly confidential - do not communicate

## Example
STAKEHOLDERS ANALYSIS
Date: 23 febb 2023
Project: Yield machine improvement | [10 empty] | Technical
|  |  | mark with an 'X' the level of project support by stakeholder | [7 empty] | Political
Role | Name | Function | Strongly against | Moderatly Against | Neutral | Moderatly Supportive | Strongly Supportive | Nature of resistance (Technical, Political, Cultural, Personal) | Influence (High,Medium, Low) | Influence strategy | Cultural
Sponsor | Mrs … | VP Operations |  |  |  |  | X |  |  |  | Personal
Financial Controller | Mr … | Head of Finance controlling |  |  | X | [5 empty] | Low
Stakeholder 1 | Mrs … | CIO | X |  |  |  |  | Political | Medium | Communicate regularly the project status and progress | Medium
Stakeholder 2 | Mr … | COO |  | X |  |  |  | Cultural | High | Keep him involved in the project by asking his/her validation on all our actions/deliverables and especially the ones that will impact him/her. Communiquer avancement et résultats dès qu'il y a succès et amélioration. Communicate regularly the project status and progress. | High
Stakeholder 3 | Mrs… | CTO |  |  | X |  |  |  | Low
Stakeholder 4 | Mr … | VP HR |  |  | X |  |  |  | Low
Stakeholder 5 | Mrs … | General Manager AMER |  | X |  |  |  | Cultural | Medium | Keep him involved in the project by asking his/her validation on all our actions/deliverables and especially the ones that will impact him/her. Communiquer avancement et résultats dès qu'il y a succès et amélioration. Communicate regularly the project status and progress.
Process Owner | Mr … | Production Manager |  |  |  |  | X
Team member 1 | Mrs… | Engineer |  |  | X |  |  | Technical | High | Enroll him in the next Green Belt Training
Team member 2 | Mr … | Technician |  | X |  |  |  | Cultural | Medium | Enroll him in the next Green Belt Training. Decrease his workload
Team member 3 | Mrs… | Supervisor |  | X |  |  |  | Cultural | Medium | Enroll him in the next Green Belt Training
Team member 4 | Mr… | Technician | X |  |  |  |  | Technical | Low | none
Team member 5
Highly confidential - do not communicate